## BARD Equipment Work Order Detai
Equipment Work Order Detail
Filters: Equipment - 8236 2002 DEISTER 4 X 14 - SAND PLANT [02. 7.8236]; Show labor - Yes; Show parts - Yes
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
4063 |  | Welded flag holders on legs of plant wheels |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2019-12-03 09:26 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
5443 | Welded flag holders on legs of plant wheels |  |  | Proactive Repair | Conveyor / Screener / Stacker |  | Conveyor |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | In Process |  | 2019-12-03 07:53 | Lynn Schmitz |  |  |  | Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 4063 Total Cost |  |  |  | 0 | 20 |  |  |  |  | 20
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
4571 |  | replaced to deck crown bar assy. |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2019-12-13 12:32 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
6115 | corrective maintenance |  |  | Proactive Repair | Frame / Crossmember |  | Frame |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2019-12-13 | Tracy Deutmeyer
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 4571 Total Cost |  |  |  | 0 | 3409.8 |  |  |  |  | 3409.8
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
6407 |  | new screen order |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Travis Kieler | 2020-02-20 10:30 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
9050 | new screen order |  |  | New Component | Conveyor / Screener / Stacker |  | Screens |  |  | New Equipment Setup | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-02-17 13:14 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 6407 Total Cost |  |  |  | 0 | 5840 |  |  |  |  | 5840
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
7137 |  | new screens |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Travis Kieler | 2020-03-24 07:09 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
10237 | new screens |  |  | New Component | Conveyor / Screener / Stacker |  | Screens |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-03-24 07:07 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 7137 Total Cost |  |  |  | 0 | 1570 |  |  |  |  | 1570
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
7395 |  | screens |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Travis Kieler | 2020-04-01 13:01 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
10586 | screens |  |  | New Component | Conveyor / Screener / Stacker |  | Screens |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-03-27 05:18 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 7395 Total Cost |  |  |  | 0 | 5355 |  |  |  |  | 5355
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
7821 |  | 2" ball valves |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2020-04-15 12:03 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
11203 | 2" ball valves |  |  | New Component | New Equipment Setup |  | New Equipment Setup |  |  | New Equipment Setup | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-04-23 09:44 | Travis Kieler |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | 2"ball valve |  |  | 4 |  |  | EACH |  |  | 50 |  | 200
|  |  | Total Work Order Item Part Cost [11203] | [10 empty] | 200
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Stephen Weydert |  |  | 2020-04-15 |  |  | replac ball valves |  |  | 0.75 |  |  | RC1 |  | 22.5
|  |  | Total Work Order Item Labor Cost [11203] | [5 empty] | 0.75 |  |  |  |  | 22.5
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 7821 Total Cost |  |  |  | 22.5 | 200 |  |  |  |  | 222.5
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
8268 |  | went to stevens sand pit looked at screen deck |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2020-04-30 07:07 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
11829 | went to stevens sand pit looked at screen deck |  |  | Proactive Repair | Conveyor / Screener / Stacker |  | Screens |  |  | Normal Wear and Tear | Fabricated / Welded |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-04-29 | Brian Thornton |  |  |  | Not Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 8268 Total Cost |  |  |  | 240 | 0 |  |  |  |  | 240
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
8712 |  | replace motor mount bracket on screen deck |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2020-05-07 16:49 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
12464 | replace motor mount bracket on screen deck |  |  | Reactive Repair / Emergency Breakdown | Conveyor / Screener / Stacker |  | Other |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | In Process |  | 2020-05-07 10:10 | Travis Kieler |  |  |  | Not Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 8712 Total Cost |  |  |  | 60 | 0 |  |  |  |  | 60
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
8812 |  | motor mount on screen |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Travis Kieler | 2020-05-19 07:03 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
12607 | motor mount on screen |  |  | New Component | Conveyor / Screener / Stacker |  | Other |  |  | Other | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2020-05-19 06:39 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 8812 Total Cost |  |  |  | 0 | 300 |  |  |  |  | 300
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
16097 |  | 2021 Repairs and Maintenance |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Tracy Deutmeyer | 2021-01-18 10:03 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23308 | Replace Sub Deck Top |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23309 | Reline Discharge Box |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23310 | Line Up Pins |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23311 | Service Boxes |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23312 | Change Oil In Screen Box |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
23313 | Reline Under Screen Box |  |  | Preventative Maintenance | Production Equipment |  | Screens |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-01 | B2W Admin
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 16097 Total Cost |  |  |  | 0 | 0 |  |  |  |  | 0
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
16615 |  | winter maintenance |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2021-02-09 16:11 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
24864 | winter maintenance |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-02-08 09:40 | Travis Kieler |  |  |  | Not Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 16615 Total Cost |  |  |  | 5427.5 | 0 |  |  |  |  | 5427.5
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
17678 |  | TIRE REPAIR--POMPS |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Brandon Zasada | 2021-04-02 11:22 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
26922 | TIRE REPAIR--POMPS |  |  | Reactive Repair / Emergency Breakdown | Tires / Wheels |  | Tires - All |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-04-02 | Brandon Zasada
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 17678 Total Cost |  |  |  | 0 | 170 |  |  |  |  | 170
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
18562 |  | New screens |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Travis Kieler | 2021-05-06 06:41 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
28172 | New screens |  |  | New Component | Conveyor / Screener / Stacker |  | Screens |  |  | Other | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-05-06 05:54 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 18562 Total Cost |  |  |  | 0 | 780 |  |  |  |  | 780
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
21075 |  | LEFT REAR HUB CAP LEAKING |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Brandon Zasada | 2021-07-26 15:05 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
31218 | LEFT REAR HUB CAP LEAKING |  |  | Reactive Repair / Emergency Breakdown | Drivetrain |  | Other |  |  | Normal Wear and Tear | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2021-07-26 | Brandon Zasada
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
3434249 |  |  | HUB CAP WITH PIPE PLUG |  |  | 1 |  |  | EACH |  |  | 47.663 |  | 47.663
SHOPSUPP |  |  | SHOP SUPPLIES |  |  | 2 |  |  | EACH |  |  | 20 |  | 40
|  |  | Total Work Order Item Part Cost [31218] | [10 empty] | 87.663
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Ross Kuhlman |  |  | 2021-07-26 |  |  | REPLACED HUB CAP |  |  | 1 |  |  | RC1 |  | 65
|  |  | Total Work Order Item Labor Cost [31218] | [5 empty] | 1 |  |  |  |  | 65
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 21075 Total Cost |  |  |  | 65 | 87.663 |  |  |  |  | 152.663
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
23831 |  | 8236 2021-2022 Winter Maintenance |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | B2W Admin | 2021-10-27 14:02 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
34883 | 2021-2022 Winter Maintenance |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  |  |  | 2022-01-07 08:41 | Travis Kieler
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | 2"ball valve |  |  | 1 |  |  | EACH |  |  | 42 |  | 42
|  |  | MISC SHOP |  |  | 1 |  |  | EACH |  |  | 80 |  | 80
|  |  | Service work to pan |  |  | 0 |  |  | EACH |  |  | 50 |  | 0
|  |  | steel for waste chutes |  |  | 1 |  |  | EACH |  |  | 916.19 |  | 916.19
|  |  | Total Work Order Item Part Cost [34883] | [10 empty] | 1038.19
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Stephen Weydert |  |  | 2022-01-05 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Stephen Weydert |  |  | 2022-01-03 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Cody Dettbarn |  |  | 2022-01-05 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Stephen Weydert |  |  | 2022-01-04 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Stephen Weydert |  |  | 2022-01-06 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Cody Dettbarn |  |  | 2022-01-03 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 585
Cody Dettbarn |  |  | 2022-01-06 |  |  | winter maintenance |  |  | 5 |  |  | RC1 |  | 325
|  |  | Total Work Order Item Labor Cost [34883] | [5 empty] | 59 |  |  |  |  | 3835
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
34884 | LABOR/TIME |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  |  |  | 2022-01-07 08:41 | Travis Kieler
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 23831 Total Cost |  |  |  | 3835 | 1038.19 |  |  |  |  | 4873.19
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
25685 |  | finished hared facing on screen plant |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2022-01-07 14:28 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
37662 | finished hared facing on screen plant |  |  | Proactive Repair | Production Equipment |  | Other |  |  | Normal Wear and Tear | Fabricated / Welded |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2022-01-06 | Brian Thornton |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | Post alloy hard face wire |  |  | 10 |  |  | EACH |  |  | 14 |  | 140
|  |  | Total Work Order Item Part Cost [37662] | [10 empty] | 140
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Paul Ling |  |  | 2022-01-06 |  |  | finished hared facing on screen plant |  |  | 6 |  |  | RC1 |  | 390
|  |  | Total Work Order Item Labor Cost [37662] | [5 empty] | 6 |  |  |  |  | 390
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 25685 Total Cost |  |  |  | 390 | 140 |  |  |  |  | 530
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
26028 |  | started working on sand plant |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2022-01-07 10:20 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
38404 | started working on sand plant |  |  | Proactive Repair | Production Equipment |  | Other |  |  | Normal Wear and Tear | Repaired / Replaced |  | None |  | 925 Dubuque South Shop
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2022-01-31 | Brian Thornton |  |  |  | Not Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 26028 Total Cost |  |  |  | 325 | 0 |  |  |  |  | 325
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
27227 |  | replace damaged hub cap on screen legs |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2022-04-06 11:53 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
40562 | replace damaged hub cap on screen legs |  |  | Reactive Repair / Emergency Breakdown | Tires / Wheels |  | Wheel / Rim |  |  | Other | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2022-04-06 13:31 | Travis Kieler |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | axle bearing gear lube 1607 |  |  | 1 |  |  | PT |  |  | 5 |  | 5
|  |  | skf hub cap |  |  | 1 |  |  | EACH |  |  | 35 |  | 35
|  |  | Total Work Order Item Part Cost [40562] | [10 empty] | 40
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Stephen Weydert |  |  | 2022-04-06 |  |  | hub cap replacement |  |  | 0.5 |  |  | RC1 |  | 17.5
|  |  | Total Work Order Item Labor Cost [40562] | [5 empty] | 0.5 |  |  |  |  | 17.5
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 27227 Total Cost |  |  |  | 17.5 | 40 |  |  |  |  | 57.5
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
31448 |  | screen |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | B2W Admin | 2022-08-23 15:35 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
46210 | screen |  |  | Proactive Repair | Conveyor / Screener / Stacker |  | Screens |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2022-08-23 | B2W Admin
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 31448 Total Cost |  |  |  | 0 | 1755 |  |  |  |  | 1755
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
33122 |  | SPRING |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | B2W Admin | 2022-10-13 15:55 |  | Transferred |  | Blank
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
48429 | SPRING |  |  | Proactive Repair | Production Equipment |  | Other |  |  | Other | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2022-10-13 | B2W Admin
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 33122 Total Cost |  |  |  | 0 | 1085.7 |  |  |  |  | 1085.7
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
36364 |  | started working on sand plant |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2023-02-26 19:26 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
53085 | started working on sand plant |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Repaired / Replaced |  | None |  | 925 Dubuque South Shop
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2023-02-27 | Brian Thornton |  |  |  | Not Covered by Warranty
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 36364 Total Cost |  |  |  | 871.25 | 0 |  |  |  |  | 871.25
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
36393 |  | winter maintenance |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2023-02-24 15:00 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
53124 | winter maintenance |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Preventive Maintenance Completed |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2023-02-27 15:05 | Travis Kieler |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | coil spring 11 coils |  |  | 1 |  |  | EACH |  |  | 275 |  | 275
|  |  | utechtic plate 1X2'X1/4 |  |  | 1 |  |  | EACH |  |  | 250 |  | 250
|  |  | shop supplies |  |  | 1 |  |  | EACH |  |  | 100 |  | 100
LE6407 |  |  | LE-6407 COMPRESSOR/TURBINE OIL |  |  | 25 |  |  | QT |  |  | 10.8416 |  | 271.04
|  |  | Total Work Order Item Part Cost [53124] | [10 empty] | 896.04
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Stephen Weydert |  |  | 2023-02-27 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 765
Vince Averkamp |  |  | 2023-02-27 |  |  | winter maintenance |  |  | 9 |  |  | RC1 |  | 765
Vince Averkamp |  |  | 2023-02-24 |  |  | winter maintenance |  |  | 8 |  |  | RC1 |  | 680
Stephen Weydert |  |  | 2023-02-24 |  |  | winter maintenance |  |  | 8 |  |  | RC1 |  | 680
|  |  | Total Work Order Item Labor Cost [53124] | [5 empty] | 34 |  |  |  |  | 2890
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 36393 Total Cost |  |  |  | 2890 | 896.04 |  |  |  |  | 3786.04
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
36538 |  | hard faced rock box for sand plant |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Paul Ling | 2023-03-05 14:29 |  | Transferred |  | Shop
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
53343 | hard faced rock box for sand plant |  |  | Preventative Maintenance | Annual Inspections / Winter Maintenance |  | Annual Inspections / Repairs |  |  | Preventive Maintenance | Repaired / Replaced |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2023-02-27 | Brian Thornton |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | 1/4 postal hard facing rod 5 ponds |  |  | 5 |  |  | EACH |  |  | 15 |  | 75
|  |  | Total Work Order Item Part Cost [53343] | [10 empty] | 75
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Paul Ling |  |  | 2023-02-27 |  |  | hard faced rock box for sand plant |  |  | 10.5 |  |  | RC1 |  | 892.5
|  |  | Total Work Order Item Labor Cost [53343] | [5 empty] | 10.5 |  |  |  |  | 892.5
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 36538 Total Cost |  |  |  | 892.5 | 75 |  |  |  |  | 967.5
Work Order ID |  | Description |  | Equipment ID | Equipment Description |  |  | Priority Name |  | Created By | Created On |  | Status Name |  | Planned Work Location
36656 |  | A1 crane set up |  | 02. 7.8236 | 8236 2002 DEISTER 4 X 14 - SAND PLANT |  |  | Low |  | Steve Weydert | 2023-03-08 15:49 |  | Transferred |  | Field
Work Order Item ID | Work Order Item Description |  |  | Type | Component |  | Subcomponent |  |  | Failure | Action |  | Problem |  | Work Location
53501 | A1 crane set up |  |  | Proactive Repair | Production Equipment |  | Screens |  |  | Preventive Maintenance | Adjusted / Aligned |  | None
Job ID | Job Descriptiton |  |  | Tracking Account ID | Tracking Account Description |  |  | Item Condition |  | Completion Date | Completed By |  | Completion Meter Reading |  | Warranty
- | - |  |  | - | - |  |  | Complete |  | 2023-03-08 15:57 | Travis Kieler |  |  |  | Not Covered by Warranty
Work Order Item Parts
Part ID |  |  | Part Description |  |  | Quantity |  |  | UM |  |  | Unit Price |  | Part Cost
|  |  | A 1 Crane service |  |  | 1 |  |  | EACH |  |  | 630 |  | 630
|  |  | Total Work Order Item Part Cost [53501] | [10 empty] | 630
Work Order Item Labor
Employee |  |  | Date |  |  | Labor Description |  |  | Labor Hours |  |  | Labor Rate |  | Labor Cost
Stephen Weydert |  |  | 2023-03-08 |  |  | set up |  |  | 1 |  |  | RC1 |  | 85
|  |  | Total Work Order Item Labor Cost [53501] | [5 empty] | 1 |  |  |  |  | 85
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Work Order 36656 Total Cost |  |  |  | 85 | 630 |  |  |  |  | 715
|  |  |  | Total Labor Cost | Total Part Cost |  |  |  |  | Total Cost
Total Cost |  |  |  | 15121.25 | 23392.393 |  |  |  |  | 38513.643